| # Regional Director - Responsibilties | When |
| --- | --- |
| - Schedule tournament dates in conjunction with RAD council. - Meet with RAD council for planning the RAD event and submit budget. | one year in advance - at fall meeting |
| - Arrange for a tournament director. - Arrange for quiz masters and secure commitment. | by January by January |
| Meet with the RAD/180 council for planning for the RAD event. Provide a budget for the RAD Council. | Spring meeting |
| Order the following: - Regional tournament questions for tournment director - six trophies - one for each of the top three teams for each division (District Champions and All-Stars) engraved appropriately, - metals (or trophies) -one for each member of the six teams above, and - 20 color certificates with place for names one for each quizzer in the Top Ten of each division. | March |
| Arrange for a tournament schedule that meshes with the RAD activities. |  |
| # Tournament Director - Responsibilties |  |
| - Mail out rule clarification sheet to all district leaders. - Mail out rule clarification sheet and intro letter to all quiz masters . | before January April |
| Prepare tournament handbook: - get current NYI logo, - assign rooms to quiz masters, content judges and score keepers, - set up the tournament schedule including times, locations and teams for each round and - add names and addresses of all quizzers, coaches, district leaders as available. - Meet with quiz masters prior to the tournament to explain and discuss rules interpretations. - Meet with leaders/captains at the start of the tournament to explain and discuss rules interpretations. | Start in April, finish as names are available7:00am 1st day7:30am 1st day |
| - Arrange for statistican for summarizing scoring and runner (score sheets to statistican, water to the rooms, etc.). - Put together quiz master packets (scripture portion marked with key words, concordance, regional tournament questions, scoresheets, pencils and copy of the rules). |  |
| - Be a quiz master, if necessary. |  |
| # Facilities Coordinator - Responsibilties |  |
| - Check with College church to arrange for rooms. - Check with NNU representative to arrange special food and room assignments. | before March by March |
| Arrange for equipment for the tournament: - call Education Media at NNU for micro phones and tape players in each room and - make sure enough jump lights are coming (number of quiz rooms +1) |  |
| - Reserve quiz areas (Franklin Hall) and send requirements to person in charge of room set up. |  |